## Cover
QA Report
Sprint | : | 1
Project | : | Data for Road Incident Visualization Evaluation and Reporting (DRIVER)
Build | : | V-1.0
Date | : | 2023-09-27
Reporter | : | Arifa Akter

## Release Summary
Project Name Release Summary Report
Release Info |  | Browser & Device List
Release Name | WK-1 | # | Tested Device Name & Model[Windows] | Version
Version Name | V-1.0 | 1 | Laptop/PC [Windows] | Win-10
|  | # | Desktop web Browser | Version
Release Topic | 1. Login 2. Dashboard 3. My Account 4. Managed Duplicate Records 5. Map 6. Record List 7. Add a Record | 1 | Windows-Chrome | 116.0.5845.188
Start Date | 18-09-2023
End Date | 27-09-2023
QA Release Date | 27-09-2023
Release Status | N/A
Released By | Arifa Akter
Prepared By | Arifa Akter
Verified By | Abdul Qadir
Executed Test Type:
1 | Functional Test
2 | UI Test
Non Executed Test Type:
1 | Retest
2 | Regression
3 | Security
4 | Virus Checking
5 | Reliability
6 | Usability
7 | Performance
8 | Device compatibility
9 | Responsive

## Functionality Verification
Project Name Release Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | SE/TL Comment | QA Comment
1 | Login | Yes | Yes | OK
2 | Dashboard | Yes | Yes | NG |  | Bug #479558 Bug #479874 Bug #479878
3 | My Account | Yes | Yes | OK
4 | Managed Duplicate Records | Yes | Yes | NG |  | Bug #479465
5 | Map | Yes | Yes | NG |  | Bug #479454 Bug #479584 Bug #479857
6 | Record List | Yes | Yes | OK
7 | Add a Record | Yes | Yes | NG |  | Bug #479536 Bug #479861 Bug #479862 Bug #479863 Bug #479882
[N.B: We have checked all screens and found some major and minor issues, these are posted in Redmine]

## Graphical Report
Test Case Execution Report
| Build Version No: | V-1.0
| Total Test cases: | 99
| Test Environments (Browsers): | 1
| Total Executable test cases: | 99
| Test Cases Executed: | 94
| Passed: | 82
| Failed: | 12
| NE: | 0
| NA: | 5
| WIP: | 0
| Total Reported Bugs : | 11
| New | 0
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 11
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Blocker | 0
| Critical | 0
| Major | 1
| Minor | 10
| Trivial | 0
| Total: | 11
| Reported Bugs : (All Sprints) | 10
| New | 0
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 10
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Low | 8
| Medium | 3
| High | 1
| Urgent | 0
| Immediate | 0
| Total: | 12
Step-2: Sprint#1 Bug summary
Step-2: Sprint#1 Bugs Severity:
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
Sprint# Bug List
Bug Type | Quantity
UI: | 3
Functional: | 9
Total: | 12
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | https://redmine.bjitgroup.com/redmine/issues/479584 | [v-1.0][Map] By clicking on the Total economic loss and societal harm tab of the map’s footer section, the collision of motor amount is not properly showing in the pop-up. | Open | Minor | Minor
2 | https://redmine.bjitgroup.com/redmine/issues/479862 | [v-1.0][Add a Record] In Incident Images filed, Image Title Remains After Deleting Image Using Cross Icon. | Open | Minor | Minor
3 | https://redmine.bjitgroup.com/redmine/issues/479863 | [v-1.0][Add a Record] After deleting an image and subsequently re-uploading an image, the title field displays "No file chosen," even when an image is present. | Open | Minor | Minor
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | https://redmine.bjitgroup.com/redmine/issues/479558 | [v-1.0][Dashboard]Despite being all Thana was selected, Records of incident for last two weeks on the Dashboard page doesn't show any blue dots as per as user manual | Open | Major | Major
2 | https://redmine.bjitgroup.com/redmine/issues/479874 | [v-1.0][Dashboard] Incident Number Missing for 90 Days Despite Economic Loss and Event Count Displayed | Open | Medium | Medium
3 | https://redmine.bjitgroup.com/redmine/issues/479878 | [v-1.0][Dashboard] Black spots based on incidents are not appearing on the black spot severity section on the dashboard even though All Thana selected. | Open | Medium | Medium
4 | https://redmine.bjitgroup.com/redmine/issues/479465 | [v-1.0][Managed_Duplicate_Records] Despite duplicate records existing in Record List based on the same incident's date, time, and location within a specific range, no duplicate records are displayed on the "Potential Duplicate Records" page. | Open | Major | Major
5 | https://redmine.bjitgroup.com/redmine/issues/479455 | [v-1.0][Map]Accept future dates inputs for both "Occurred Date" and "Created Date" when applying filters on the map. | Open | Minor | Minor
6 | https://redmine.bjitgroup.com/redmine/issues/479857 | [v-1.0][Map] Accepts fractional (decimal) numbers in the "Age" field when the filter is saved without throwing an error or warning. | Open | Minor | Minor
7 | https://redmine.bjitgroup.com/redmine/issues/479882 | [v-1.0][Add a Record] Multiple images cannot be uploaded consecutively in the INCIDENT IMAGES section of the Add a Record page. | Open | Minor | Minor
8 | https://redmine.bjitgroup.com/redmine/issues/479536 | [v-1.0][Add a Record] Unable to immediately re-upload same image in INCIDENT IMAGES field after deleting it once by using (x) icon. | Open | Medium | Medium
9 | https://redmine.bjitgroup.com/redmine/issues/479861 | [v-1.0][Add a Record] Infinite number of characters enter into "LOCATION NAME OF CITY/TOWN/VILLAGE / নগর/শহর/গ্রামের অবস্থানের নাম" and "LOCATION NAME OF ROAD / সড়কের অবস্থানের নাম" text fields. | Open | Minor | Minor
Functional Bugs:
Step-2: Sprint#3- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
Sprint#1 | 90 | 10 | 0 | 0

## Defect density
Sprint | Effort | Defect | Defect density | Defect density
Sprint#1 | 1 | 0 | 0% | 0%